SkillProof AI

An AI-Validated, Industry-Grade Upskilling & Assessment Platform

for CSE, IT, AI/ML and Core Engineering (ECE, EEE, Mechanical, Automobile) Students

Technical Architecture, Product Plan, Statement of Work & Sprint Roadmap

Prepared for: Development Team • Industry Expert Panel • Business Stakeholders

Version 1.0

# Table of Contents

Table of Contents	2

1. Executive Summary	5

2. Problem Statement, Vision & Differentiation	6

2.1 The problem	6

2.2 Vision	6

2.3 Differentiation matrix	6

3. Users, Personas & Domain Coverage	7

3.1 Primary personas	7

3.2 Branch → assessment-type mapping	7

4. Platform Features — End-to-End Walkthrough	9

4.1 Student journey	9

4.2 Project catalog & content engine	9

4.3 AI Assessment Engine (core differentiator)	9

4.4 Human Expert Validation Layer	10

4.5 Company Partner Portal	10

4.6 College / Placement Cell Console	10

4.7 Admin / Ops Console	10

4.8 Gamification, portfolio & credentialing	10

5. AI Assessment Engine — Domain-Specific Design	12

5.1 Common intake pipeline (all branches)	12

5.2 CSE / IT pipeline	12

5.3 AI/ML & Data Science pipeline	12

5.4 Core engineering pipeline (ECE / EEE / Mechanical / Automobile)	13

5.5 Scoring model & AI/human weighting	13

5.6 Continuous calibration loop	13

6. Human Expert Validation — Workflow & Governance	14

6.1 Expert lifecycle	14

6.2 Review assignment logic	14

6.3 Review console requirements	14

6.4 Dispute resolution	14

7. Technical Architecture	15

7.1 Architectural style	15

7.2 High-level component map	15

7.3 Core domain services	15

7.4 Assessment pipeline — event flow	16

7.5 Recommended technology stack	16

7.6 Core data entities (conceptual data model)	17

7.7 Integrations	17

8. Non-Functional Requirements	19

8.1 Security & integrity	19

8.2 Data privacy & compliance	19

8.3 Scalability & performance	19

8.4 Reliability	19

8.5 Auditability	19

8.6 Cost governance	19

9. Team Structure (Build Phase)	19

10. Statement of Work (SOW)	21

10.1 Purpose & scope of this SOW	21

10.2 In-scope deliverables	21

10.3 Out of scope (this phase)	21

10.4 Assumptions & dependencies	21

10.5 Acceptance criteria (platform-level, applies across releases)	22

10.6 Milestone-based delivery structure	22

10.7 Payment-milestone template (for business owner – vendor/contract use)	22

10.8 Change management	23

11. Sprint-Based Delivery Plan	24

11.1 Release R0 — Foundation (Sprints 0–2)	24

11.2 Release R1 — CSE/IT MVP (Sprints 3–7)	24

11.3 Release R2 — AI/ML & Data Science track (Sprints 8–10)	24

11.4 Release R3 — Core Engineering tracks (Sprints 11–16)	24

11.5 Release R4 — Expert & Company ecosystem (Sprints 17–19)	25

11.6 Release R5 — Credentialing, analytics & scale hardening (Sprints 20–22)	25

11.7 Parallel workstream — content & expert governance	25

12. Risks & Mitigations	27

13. Success Metrics (KPIs)	27

13.1 Product/engagement KPIs	27

13.2 Quality/trust KPIs	27

13.3 Business KPIs	27

14. Glossary	28

# 1. Executive Summary

Colleges produce graduates who clear exams but arrive at their first job unable to ship production code, defend an engineering design decision, or work inside a real constraint set (cost, safety, standards, security). Recruiters currently re-train every hire for 3–6 months before they become productive. SkillProof AI closes that gap by replacing academic-style assessment with real, time-boxed, industry-grade project work that is scored the way a company would actually evaluate it — by an AI assessment engine, backed by human industry experts, using rubrics that companies themselves can contribute.

What makes this different from LeetCode / HackerRank / HackerEarth

- Those platforms test isolated algorithmic problems in a browser IDE. SkillProof AI issues full-scope projects (a feature to build, a circuit to design, a machine to model, a dataset to productionize) that mirror an actual sprint ticket or R&D brief.

- Assessment is multi-dimensional — code quality, architecture, security posture, test coverage, and (for core branches) design correctness, simulation results, and safety/standards compliance — not just “output matches expected output.”

- Every branch (not just CSE/IT) gets a first-class assessment pipeline: ECE/EEE circuit and simulation review, Mechanical/Automobile CAD, FEA/simulation and design-report review.

- AI does the first pass at scale; certified industry experts calibrate, override, and sign off — so a score on the platform carries real credibility with employers.

- Companies can publish their own project briefs and rubrics directly, turning the platform into a sourcing and pre-screening channel for hiring, not just a learning tool.

Who this document is for

- Development team — Sections 4–9 (architecture, data model, tech stack, sprint plan) are the build spec.

- Industry experts — Sections 3, 5, and 6 (assessment methodology per domain, expert validation workflow) need their sign-off before build starts.

- Business owner — Sections 1, 2, 10 and 11 (vision, business model implications, SOW, KPIs, risks) frame the investment case.

Read this first This is a build-ready specification, not a pitch deck. Assumptions that materially affect cost or timeline are called out explicitly in Section 10 (SOW) so they can be validated or corrected before Sprint 0 begins.

# 2. Problem Statement, Vision & Differentiation

## 2.1 The problem

Academic curricula are evaluated on syllabus completion and exam recall. Industry hires on demonstrated ability to build, debug, secure, and defend a working solution under real constraints. The result is a structural mismatch: strong CGPA does not predict on-the-job capability, and companies have no fast, trustworthy signal to identify job-ready candidates without running their own lengthy hiring pipelines.

## 2.2 Vision

Become the trust layer between colleges and industry: a place where a student’s score is a verifiable, defensible statement of “this person can do the job,” validated jointly by AI and practicing industry professionals, and where companies can source, brief, and pre-vet candidates directly.

## 2.3 Differentiation matrix

| Dimension | LeetCode / HackerRank / HackerEarth | SkillProof AI |
| --- | --- | --- |
| Task type | Isolated algorithm/DSA problems | Full project briefs mirroring real sprint tickets / R&D tasks |
| Branches covered | CSE/IT only | CSE, IT, AI/ML, ECE, EEE, Mechanical, Automobile |
| Assessment depth | Test-case pass/fail on function output | Code quality, architecture, security, tests, docs, design correctness, simulation validity |
| Human involvement | Little to none | Certified industry experts calibrate AI scores and can override |
| Time model | Minutes, live in-browser IDE | 48-hour offline, real-world build-and-submit cycle |
| Source of content | Platform-authored puzzles | Platform + industry experts + companies directly publish briefs |
| Output for student | Rating/badge | Verifiable scorecard + portfolio + employer-facing credential |
| Output for company | None | Direct access to pre-vetted, scored talent pool and custom assessment channel |

# 3. Users, Personas & Domain Coverage

## 3.1 Primary personas

Student (CSE / IT)

Wants real projects that look good on a resume, clear rubric-based feedback, and a credential recruiters trust.

Student (AI/ML & Data Science)

Needs datasets and problem framings that resemble production ML work — not Kaggle leaderboard toy problems — with evaluation on generalization, reproducibility, and responsible-AI practices.

Student (Core engineering — ECE, EEE, Mechanical, Automobile)

Currently has almost no equivalent of LeetCode. Needs design/simulation/build tasks assessed against real industry design standards, safety margins, and cost/manufacturability constraints.

Industry Expert / Validator

A practicing engineer or senior professional who reviews AI-flagged or randomly-sampled submissions, corrects/confirms AI scoring, and authors or reviews new project briefs and rubrics. Paid per review or via a revenue-share/gig model.

Company Partner

Publishes proprietary or representative project briefs (with NDA/IP protection), defines or approves the rubric, and gets a ranked, scored shortlist of candidates — effectively a pre-screening and employer-branding channel.

College / Placement Cell (secondary persona)

Bulk-enrolls a cohort, tracks branch-wise readiness, and uses aggregate analytics for placement conversations with recruiters.

Platform Admin / Ops

Manages project catalog, expert pool, dispute resolution, plagiarism/integrity cases, and platform health.

## 3.2 Branch → assessment-type mapping

| Branch | Deliverable format | Primary automated checks |
| --- | --- | --- |
| CSE / IT | GitHub repo (code + README + tests) | Static analysis, unit/integration test execution, security scan (SAST/dependency), style, LLM code review |
| AI/ML & Data Science | Repo + notebook + model artifact + report | Notebook execution, holdout-set metrics, data leakage checks, reproducibility, bias/robustness checks, LLM report review |
| ECE | Design report + schematic + simulation files + demo video | Schematic/netlist parsing, simulation-output validation, LLM review of design report against spec, vision-model schematic check |
| EEE | Design report + simulation (e.g. load-flow, protection) + demo/video | Simulation-result validation against tolerance, standards-compliance checklist, LLM report review |
| Mechanical | CAD file + FEA/simulation report + drawing (GD&T) + BOM | CAD/drawing parsing, FEA result validation, tolerance/standard checklist, LLM report review |
| Automobile | CAD/simulation + design report + (optional) test data | Same pipeline as Mechanical, plus automotive-standard checklist (safety, emissions, etc.) |

Core-branch submissions are inherently harder to fully automate than software. The platform therefore uses a higher AI-assist / higher human-expert-weight ratio for ECE/EEE/Mechanical/Automobile than for CSE/IT (see Section 5.4 scoring-weight table).

# 4. Platform Features — End-to-End Walkthrough

## 4.1 Student journey

- 1. Onboarding — branch, year, skill-level self-assessment, resume/GitHub import.

- 2. Skill-gap diagnostic — short adaptive quiz + resume/GitHub scan to recommend a starting track and difficulty tier.

- 3. Project assignment — student picks or is assigned a project from the catalog (filtered by branch, difficulty, industry domain, and — where applicable — a live company brief).

- 4. 48-hour build window — offline/local build; countdown timer starts on acceptance; spec, starter repo/template, and rubric are visible upfront (no black-box grading).

- 5. Submission — GitHub repo link (preferred), or direct zip/file upload with structured metadata form (README, demo video link, report as applicable).

- 6. Automated intake checks — structure validation, plagiarism/originality check, malware/secret-scan on upload, environment build sanity check.

- 7. AI assessment run — domain-specific pipeline executes (Section 5); produces a structured scorecard with sub-scores, evidence, and flags.

- 8. Expert review layer — borderline / high-stakes / randomly-sampled submissions routed to a human expert for calibration or override (Section 6).

- 9. Result — pass/fail + numeric score + rubric-level breakdown + specific improvement feedback + suggested next project.

- 10. Portfolio & credential — passed projects accumulate into a verifiable public portfolio profile with shareable credential/badge; feeds a branch-wise “industry readiness score.”

- 11. (Optional) Company visibility — student can opt in to be discoverable by company partners for the specific skills/projects they scored well on.

## 4.2 Project catalog & content engine

- Project bank tagged by: branch, sub-domain (e.g. backend/frontend/DevOps, CV/NLP/tabular-ML, analog/digital/embedded, thermal/structural/design, powertrain/EV, etc.), difficulty, estimated effort, and “real-world source” (platform-authored / expert-authored / company-contributed).

- AI-assisted project generation: an internal authoring pipeline drafts new project briefs and rubrics from real industry patterns (job descriptions, open-source issue patterns, public engineering design problems), which experts then review and approve before publishing — experts are never bypassed for new content.

- Anti-repeat / anti-leak controls: parameterized variants of each project (different datasets, different component values/specs, different constraints) so answers can't be shared across cohorts; time-boxed unique tokens per assignment.

- Versioned rubrics: every project has a machine-readable rubric (JSON) consumed by both the AI engine and the expert review UI, so AI and human scoring use the identical criteria.

## 4.3 AI Assessment Engine (core differentiator)

A domain-routed pipeline (full technical detail in Section 5) that takes a submission + its rubric and produces a structured, evidence-backed scorecard — never a single opaque number.

## 4.4 Human Expert Validation Layer

- Expert marketplace: verified industry professionals apply, get domain-tagged and credential-checked, and pick up review assignments (gig-style, paid per review or via subscription revenue share).

- Review console: side-by-side AI scorecard + submission + rubric, with agree/override/comment actions and a required justification when overriding.

- Calibration loop: expert overrides are logged and used to retrain/prompt-tune the AI engine (Section 5.5) and to compute each project's “AI-confidence” rating going forward.

- Escalation & disputes: students can appeal a score; escalates to a second expert or a panel for high-value disputes.

## 4.5 Company Partner Portal

- Company onboarding with NDA workflow for proprietary project briefs.

- Brief builder: company defines the task, constraints, and rubric (or adopts a platform template), sets an application/visibility window, and whether it's used for hiring, branding, or both.

- Talent view: ranked, filterable list of students who completed the brief, with full scorecards and (if opted in) contact/interview scheduling.

- Analytics: skill-gap heatmaps across the applicant pool, benchmark vs. platform-wide scores.

## 4.6 College / Placement Cell Console

- Cohort bulk enrollment, branch-wise “industry readiness” dashboards, exportable reports for placement drives and NBA/NAAC-style outcome evidence.

## 4.7 Admin / Ops Console

- Project & rubric lifecycle management, expert pool management and payouts, integrity/plagiarism case queue, platform health and cost monitoring (AI compute spend per assessment), content moderation.

## 4.8 Gamification, portfolio & credentialing

- Branch-wise readiness score (0–100), skill badges per sub-domain, streaks for consistency, leaderboards scoped to college/cohort (opt-in, not default-public to avoid unhealthy competition).

- Shareable, verifiable credential page (public URL + optional signed/verifiable-credential format) for each passed project and cumulative readiness score — designed to be linked from LinkedIn/resume.

Product principle Every score the platform issues must come with visible evidence (what was checked, what passed/failed, and who — AI or which expert — made the final call). This is what lets an employer trust the number instead of re-testing the candidate.

# 5. AI Assessment Engine — Domain-Specific Design

The engine is a routed pipeline: a submission enters an intake stage, is routed by branch/sub-domain to a domain evaluator, and produces a structured JSON scorecard consumed by the student UI, the expert review console, and analytics. No domain evaluator produces a bare pass/fail without evidence.

## 5.1 Common intake pipeline (all branches)

- Structure & completeness check — required files/artifacts present per the project's manifest.

- Originality/plagiarism check — code similarity (e.g. MOSS-style token matching) against prior submissions and public repos; document/report similarity check for reports.

- Secret & malware scan — uploaded artifacts scanned before anything is executed or opened.

- Sandboxed environment build — for code submissions, a containerized build/install pass with a timeout, isolated network egress, and resource limits.

## 5.2 CSE / IT pipeline

| Stage | Tooling approach | What it produces |
| --- | --- | --- |
| Static code analysis | SonarQube/Semgrep-class linting + complexity metrics | Code-quality sub-score, maintainability issues list |
| Automated test execution | Project-supplied + platform “hidden” test suite run in an isolated container | Pass/fail per test, coverage % |
| Security scan | SAST (Semgrep) + dependency/CVE scan (OWASP Dependency-Check / Trivy) + basic DAST for web apps | Vulnerability list with severity |
| Architecture & standards review | LLM-based review against the project's rubric (design patterns, API design, error handling, docs) | Narrative findings + rubric sub-scores |
| Performance/output validation | Golden-output diffing / load-test harness where applicable | Functional-correctness sub-score |

## 5.3 AI/ML & Data Science pipeline

| Stage | Tooling approach | What it produces |
| --- | --- | --- |
| Reproducibility | Notebook/script executed headless in a clean environment against a pinned environment spec | Executes cleanly Y/N, runtime, resource use |
| Held-out evaluation | Platform-held test split (never shared with students) scored automatically against declared metric | Accuracy/F1/RMSE/etc. vs. cohort benchmark |
| Data-leakage & methodology check | Automated checks (train/test overlap, target leakage patterns) + LLM review of the notebook narrative | Methodology sub-score + flags |
| Robustness & bias checks | Perturbation/adversarial slice testing, subgroup performance where relevant | Robustness sub-score |
| Report/documentation review | LLM review of the write-up against a data-science rubric (problem framing, EDA, model choice justification, limitations) | Communication sub-score |

## 5.4 Core engineering pipeline (ECE / EEE / Mechanical / Automobile)

Core-branch work is assessed through a combination of structured-artifact parsing, simulation-result validation, and LLM-based document/vision review, with a deliberately higher human-expert weighting than software tracks.

| Stage | Tooling approach | What it produces |
| --- | --- | --- |
| Artifact parsing | Parse CAD (STEP/DXF), schematic/netlist, or simulation output files for structural completeness | Completeness sub-score |
| Simulation/result validation | Compare declared simulation outputs (e.g. stress, load-flow, SPICE run) against tolerance bands defined in the rubric | Correctness sub-score + deviation report |
| Standards/checklist compliance | Rubric-driven checklist (safety margins, GD&T conventions, applicable IS/IEC/ISO clause references) | Compliance sub-score + flags |
| Vision-model review | Multimodal model reviews schematic/drawing/photo of the physical build or simulation plots for obvious design errors | Design-review notes |
| Design-report review | LLM review of the written report against rubric (assumptions stated, calculations shown, trade-offs justified) | Communication sub-score |
| Demo video (where required) | Reviewed by assigned expert (not fully automated) to confirm the artifact behaves as claimed | Human-verified functional confirmation |

## 5.5 Scoring model & AI/human weighting

| Track | AI-automated weight | Human-expert weight | Notes |
| --- | --- | --- | --- |
| CSE / IT | 75–85% | 15–25% | Human review focused on architecture judgment calls & disputed security findings |
| AI/ML & Data Science | 70–80% | 20–30% | Human review focused on methodology soundness & responsible-AI judgment |
| ECE / EEE | 45–60% | 40–55% | Human review mandatory for all passes above a safety/compliance threshold |
| Mechanical / Automobile | 40–55% | 45–60% | Human review mandatory for all passes; physical/video verification often required |

Weights are configurable per project and tighten toward more AI automation over time as expert-override data accumulates and evaluator confidence rises (see Section 5.6).

## 5.6 Continuous calibration loop

- Every expert override (agree/disagree + reason) is logged against the specific rubric line item it corrects.

- A weekly calibration job aggregates overrides per project/rubric-item to (a) tune evaluator prompts/thresholds, (b) flag rubric ambiguity for the project's original author, and (c) compute a per-project “AI confidence” score that drives how much human sampling that project needs going forward.

- Target operating model: new/updated projects start at 100% human-reviewed sampling; confidence rises → sampling rate reduces on a defined curve, never fully to zero for core-engineering safety-relevant projects.

# 6. Human Expert Validation — Workflow & Governance

## 6.1 Expert lifecycle

- Apply → credential/experience verification → domain tagging (e.g. “Embedded firmware,” “Structural FEA,” “MLOps”) → a short calibration test against gold-standard submissions → activated.

- Ongoing quality control: experts are themselves scored on agreement-with-panel-consensus and turnaround time; inactive or low-quality experts are rotated out of the active pool.

## 6.2 Review assignment logic

- Routed automatically when: AI confidence for that project/rubric-item is below threshold, the submission is a randomly-sampled QA case, the student appeals a result, or the project/track policy mandates 100% human review (e.g. all core-engineering passes).

## 6.3 Review console requirements

- Side-by-side rubric, submission artifacts (code/CAD/schematic/report/video), and the AI scorecard with evidence links.

- One-click agree per rubric line, or override with a mandatory short justification (feeds the calibration loop).

- SLA timer and queue prioritization (disputes and near-deadline reviews first).

## 6.4 Dispute resolution

- Student appeal → routed to a different expert than the original reviewer → if still contested, escalates to a 3-person panel → panel decision is final and is fed back into the calibration loop as a high-weight signal.

# 7. Technical Architecture

## 7.1 Architectural style

Cloud-native, microservices-based, event-driven for the assessment pipeline (submissions are asynchronous jobs, not request/response calls). API-first so the same backend serves the web app, a future mobile app, and company/college integrations.

## 7.2 High-level component map

- Client layer: Web app (student, expert, company, admin, college portals — role-based single app or micro-frontends), future mobile app.

- API Gateway: authentication, rate limiting, request routing to backend services.

- Core domain services (see 7.3).

- Assessment Orchestration Layer: job queue + workers that route each submission through the correct domain pipeline (Section 5).

- AI/LLM Gateway: a single internal service that all evaluators call through — centralizes model selection, prompt/version management, cost tracking, retries, and guardrails, so no service calls an external model provider directly.

- Sandboxed Execution Layer: ephemeral, network-isolated containers for running/building student code and executing notebooks.

- Data layer: relational store for transactional data, object storage for submissions/artifacts, search index for the project catalog, analytics warehouse for reporting.

- Integration layer: GitHub/GitLab OAuth + webhooks, plagiarism-check provider, CI-style sandbox runner, notification (email/SMS/push), payments (for expert payouts / company subscriptions).

## 7.3 Core domain services

| Service | Responsibility |
| --- | --- |
| Identity & Access | Auth, role-based access (student/expert/company/college/admin), SSO for colleges |
| Catalog Service | Project/rubric CRUD, versioning, tagging, search |
| Submission Service | Accepts GitHub links/uploads, validates structure, stores artifacts, emits “submission.received” events |
| Assessment Orchestrator | Routes submissions to the correct domain evaluator pipeline; tracks job state |
| Evaluator Services (x4) | CSE/IT evaluator, AI/ML evaluator, Core-engineering evaluator(s), each wrapping the tool-specific pipeline from Section 5 |
| AI/LLM Gateway | Central access point to LLM/vision models with prompt versioning, cost & safety controls |
| Scoring & Rubric Engine | Combines evaluator sub-scores + rubric weights into the final structured scorecard |
| Expert Review Service | Assignment queue, review console backend, override logging, dispute workflow |
| Credential & Portfolio Service | Builds the verifiable student profile/credential pages |
| Company Portal Service | Brief authoring, NDA workflow, talent search/filter, analytics |
| Notification Service | Email/SMS/push for deadlines, results, review assignments |
| Analytics & Reporting Service | Cohort/company/admin dashboards, KPI computation |
| Billing/Payout Service | Expert payouts, company subscription billing |

## 7.4 Assessment pipeline — event flow

- 1. Student submits (GitHub link or upload) → Submission Service validates & stores → emits submission.received.

- 2. Assessment Orchestrator consumes the event, resolves the project's rubric + branch, and enqueues jobs on the relevant evaluator queue(s).

- 3. Evaluator workers run the domain pipeline (Section 5) inside sandboxed/ephemeral compute, calling the AI/LLM Gateway for any model-based checks; each stage writes structured results back.

- 4. Scoring & Rubric Engine aggregates all stage results into one scorecard and computes AI confidence; emits assessment.completed.

- 5. If confidence is below threshold / policy mandates review, Expert Review Service creates a review task and notifies a matched expert.

- 6. On expert sign-off (or automatically, if no review required), the final scorecard is published to the student, feeds Credential/Portfolio Service, and (if applicable) the Company Portal.

- 7. All override/agreement events flow to the analytics warehouse for the calibration loop (Section 5.6).

## 7.5 Recommended technology stack

| Layer | Recommended technology | Rationale |
| --- | --- | --- |
| Frontend | React/Next.js + TypeScript, Tailwind, role-based module federation | Fast iteration, strong ecosystem, good for a multi-persona portal |
| Backend services | Node.js (NestJS) or Python (FastAPI) per service, gRPC/REST internally | Python favored for evaluator/AI-heavy services; Node/NestJS fine for CRUD-heavy services |
| Async jobs/queue | Kafka or SQS/RabbitMQ + worker pools (Celery/BullMQ) | Assessment is inherently asynchronous and needs durable retries |
| Sandboxed execution | Firecracker microVMs or gVisor-hardened containers on Kubernetes, per-job network isolation | Executing untrusted student code safely at scale |
| Relational DB | PostgreSQL (managed, e.g. RDS/Cloud SQL) | Strong relational + JSONB for flexible rubric/scorecard storage |
| Object storage | S3-compatible storage for repos/artifacts/videos | Cheap, durable, integrates with scanning tools |
| Search | OpenSearch/Elasticsearch for project catalog & talent search | Faceted filtering across branch/skill/difficulty |
| Analytics warehouse | BigQuery/Snowflake/Redshift + a BI layer (Metabase/Looker) | Cohort, company, and KPI reporting |
| AI/LLM Gateway | Provider-agnostic gateway (e.g. LiteLLM-style) in front of Claude/other model APIs, with prompt versioning | Avoid vendor lock-in, central cost/safety control |
| Code quality/security tools | Semgrep, SonarQube, OWASP Dependency-Check/Trivy, MOSS-style similarity check | Proven, integrable via CLI/API in the sandbox |
| CAD/simulation parsing | Domain libraries per format (STEP/DXF parsers, SPICE-output parsers) built as adapter modules | Core-engineering artifacts vary by tool; adapters isolate this complexity |
| Infra/DevOps | Kubernetes (EKS/GKE), Terraform, GitHub Actions/GitLab CI, Prometheus/Grafana, centralized logging (ELK/Loki) | Standard, portable, supports the scale-out sandbox workload |
| Auth | OAuth2/OIDC (Auth0/Keycloak) with GitHub/Google/college-SSO login | Needed for GitHub submission flow and college SSO |

## 7.6 Core data entities (conceptual data model)

| Entity | Key attributes |
| --- | --- |
| User | id, role(s), branch, college, verification status |
| Project | id, branch, sub-domain, difficulty, rubric_id, source (platform/expert/company), version |
| Rubric | id, project_id, criteria[] (weight, type, threshold), version |
| Submission | id, project_id, student_id, artifact_refs[], submitted_at, deadline, status |
| AssessmentRun | id, submission_id, evaluator_stage_results[], ai_confidence, status |
| Scorecard | id, assessment_run_id, sub_scores{}, final_score, pass/fail, evidence_refs[] |
| ExpertReview | id, scorecard_id, expert_id, decisions[], overrides[], justification, sla_status |
| Dispute | id, submission_id, student_id, status, resolution_panel[] |
| Credential | id, student_id, project_id/track, issued_at, public_url, verification_hash |
| CompanyBrief | id, company_id, project_id, visibility_window, nda_status, hiring_flag |
| ExpertProfile | id, user_id, domain_tags[], calibration_score, active_status |

## 7.7 Integrations

- GitHub/GitLab OAuth + webhook for repo import and commit-based submission tracking.

- Plagiarism/similarity detection provider (or self-hosted MOSS-class tool).

- Video hosting for demo submissions (e.g. Mux/Cloudflare Stream) with restricted access.

- Payment gateway for expert payouts and company subscription billing.

- Email/SMS/push notification provider.

- Optional: verifiable-credentials standard (e.g. Open Badges / W3C VC) for the credential layer.

# 8. Non-Functional Requirements

## 8.1 Security & integrity

- All student code executes in network-isolated, ephemeral sandboxes with strict CPU/memory/time limits — never on shared infrastructure that touches production data.

- Secret scanning and malware scanning run before any artifact is opened or executed.

- Plagiarism/originality detection on both code and written reports, with a visible integrity flag and escalation workflow (not silent auto-fail).

- Company-contributed briefs and any proprietary rubric content are access-controlled and covered by the platform's NDA workflow.

## 8.2 Data privacy & compliance

- Student PII, submissions, and scorecards are access-scoped by role; students explicitly opt in before company partners can see their identity or contact them.

- Data residency and retention policy defined per target market (India first — DPDP Act considerations; extend to GDPR-equivalent controls if expanding internationally).

## 8.3 Scalability & performance

- Assessment pipeline scales horizontally via the job queue/worker model; sandbox capacity auto-scales with submission volume (expect strong peaks around assignment deadlines).

- Target: AI-only evaluation stages complete within a defined SLA (e.g. under 30 minutes for CSE/IT, longer for simulation-heavy core-engineering pipelines) even under deadline-day load.

## 8.4 Reliability

- Durable job queues with retry/backoff; assessment state machine must be idempotent so a worker crash never loses or double-scores a submission.

- Defined RPO/RTO for the transactional database and object storage.

## 8.5 Auditability

- Every scorecard is fully traceable: which evaluator version, which rubric version, which AI model/prompt version, and which expert (if any) produced the final result — required both for dispute resolution and for employer trust.

## 8.6 Cost governance

- AI/LLM Gateway tracks per-assessment model spend; core-engineering and AI/ML pipelines (heavier compute) are budgeted and monitored separately from lightweight CSE/IT checks.

# 9. Team Structure (Build Phase)

Indicative team to execute the sprint plan in Section 11. Sized for a focused MVP-to-scale build, not a large enterprise program.

| Role | Count | Focus |
| --- | --- | --- |
| Product / Solution Architect | 1 | Owns this spec, cross-team decisions, rubric/data-model governance |
| Backend Engineers | 3–4 | Core services, orchestration, evaluator pipelines |
| AI/ML Engineer | 1–2 | LLM Gateway, evaluator model integration, calibration loop |
| Domain Pipeline Engineer (Core-eng) | 1 | CAD/simulation parsing adapters, ECE/EEE/Mech/Auto pipelines |
| Frontend Engineers | 2–3 | Student, expert, company, admin, college portals |
| DevOps / Platform Engineer | 1 | Kubernetes, sandbox isolation, CI/CD, observability |
| QA Engineer | 1–2 | Pipeline correctness, security testing, regression |
| UX/Product Designer | 1 | Multi-persona UX, review console, credential pages |
| Industry Content/Curriculum Lead | 1 | Coordinates expert-authored projects/rubrics per branch |
| Program/Delivery Manager | 1 | Sprint planning, stakeholder coordination with experts & business owner |

# 10. Statement of Work (SOW)

## 10.1 Purpose & scope of this SOW

This SOW defines the scope, deliverables, phased timeline, assumptions, and acceptance criteria for building and launching SkillProof AI through to a scaled multi-branch platform (Section 11 sprint plan). It is written to be handed to a development team as an actionable brief and to industry experts and the business owner as a scope-of-truth document.

## 10.2 In-scope deliverables

- Web platform covering five personas: Student, Industry Expert, Company Partner, College/Placement Cell, Admin.

- Assessment Orchestration Layer and four evaluator pipelines: CSE/IT, AI/ML & Data Science, and Core Engineering (ECE, EEE, Mechanical, Automobile share one configurable pipeline with branch-specific adapters).

- AI/LLM Gateway with prompt/version management and cost tracking.

- Sandboxed execution environment for code/notebook execution.

- Expert Review console, calibration loop, and dispute-resolution workflow.

- Company Partner brief-authoring and talent-search portal, with NDA workflow.

- Credential/portfolio pages (public, shareable, verifiable).

- Analytics dashboards for admin, college, and company personas.

- Initial seeded project catalog (target counts per Section 11 phase) authored jointly by the content team and reviewing industry experts.

## 10.3 Out of scope (this phase)

- Native mobile apps (web is mobile-responsive; native app is a post-scale-phase decision).

- Physical/hardware lab partnerships or shipping physical kits to students.

- Automated grading of live in-person interviews/vivas beyond the optional AI-assisted video review noted in Section 5.4.

- Blockchain-based credentialing (Open Badges/JSON is the default; blockchain anchoring is an optional future add-on).

- Payroll/HRMS-grade billing system — Phase 1 uses a standard payment gateway integration, not a custom finance platform.

## 10.4 Assumptions & dependencies

- Industry experts are available from Sprint 0 to review and approve rubrics/projects before each branch pipeline is built — build sequencing in Section 11 depends on this.

- A third-party plagiarism/similarity-detection provider (or a self-hosted equivalent) is licensed/selected by Sprint 2.

- Cloud infrastructure budget covers sandboxed compute at projected peak submission volume (deadline-day spikes) — to be sized once first-cohort volume is known.

- LLM/AI model API access (cost and rate limits) is budgeted separately from engineering headcount; core-engineering pipelines are more compute/LLM-intensive than CSE/IT.

- Company partners for the first pilot briefs are identified by the business owner in parallel with Phase 2/3 build.

## 10.5 Acceptance criteria (platform-level, applies across releases)

- A student can submit a project via GitHub link or upload and receive a scorecard with evidence-backed sub-scores, not just a single number.

- Every scorecard is traceable to evaluator version, rubric version, and (if applicable) reviewing expert.

- An expert can review, agree/override, and publish a result within the console without engineering support.

- A company can publish a brief, view a ranked scored talent list, and export/contact candidates who opted in.

- Core-engineering submissions above the safety/compliance threshold cannot be marked “pass” without human expert sign-off.

- Security: sandboxed execution has verified network isolation and resource limits under load/penetration testing before go-live.

## 10.6 Milestone-based delivery structure

Delivery is organized into five releases (detailed sprint-by-sprint in Section 11). Each release ends with a demo/sign-off checkpoint involving the business owner and, where the release touches assessment logic, the relevant industry experts.

| Release | Scope headline | Sign-off required from |
| --- | --- | --- |
| R0 — Foundation | Core platform, auth, catalog skeleton, infra | Dev lead + business owner |
| R1 — CSE/IT MVP | Full CSE/IT assessment pipeline live end-to-end | Business owner + CSE/IT expert panel |
| R2 — AI/ML track | AI/ML & Data Science pipeline live | AI/ML expert panel |
| R3 — Core Engineering tracks | ECE, EEE, Mechanical, Automobile pipelines live | Core-engineering expert panel |
| R4 — Expert & Company ecosystem | Expert marketplace, calibration loop, company portal | Business owner + pilot company partners |
| R5 — Scale & credentialing | Credential pages, analytics, performance hardening | Business owner |

## 10.7 Payment-milestone template (for business owner – vendor/contract use)

If this SOW is executed against an external development vendor, the following milestone-linked payment structure is suggested; percentages are illustrative and should be finalized commercially, not treated as fixed.

| Milestone | Suggested payment % |
| --- | --- |
| SOW sign-off & Sprint 0 kickoff | 10% |
| R0 Foundation accepted | 15% |
| R1 CSE/IT MVP accepted | 25% |
| R2 + R3 tracks accepted | 25% |
| R4 Expert & Company ecosystem accepted | 15% |
| R5 Scale/go-live accepted | 10% |

## 10.8 Change management

Any change to rubric methodology, branch scope, or scoring weights (Section 5.5) after a release has been signed off is treated as a change request — estimated for effort/timeline impact and re-approved by the business owner before development proceeds, since these changes affect both the AI evaluators and prior expert-calibration data.

# 11. Sprint-Based Delivery Plan

Two-week sprints, five releases, ~20 sprints (~40 weeks) from Sprint 0 to full scale. Each release ends with the sign-off checkpoint defined in Section 10.6. Team composition per Section 9; not every role is needed at full capacity in every sprint.

## 11.1 Release R0 — Foundation (Sprints 0–2)

| Sprint | Goals | Key deliverables |
| --- | --- | --- |
| Sprint 0 (Discovery) | Finalize rubric taxonomy, data model, infra decisions; convene first industry-expert panel | Signed-off data model & rubric JSON schema; cloud environment provisioned; expert panel onboarded for CSE/IT & AI/ML |
| Sprint 1 | Auth/identity, base API gateway, project catalog skeleton | Login (student/expert/admin roles), catalog CRUD (no evaluators yet), CI/CD pipeline live |
| Sprint 2 | Submission Service + sandbox execution environment (proof of concept) | GitHub-link submission intake; isolated sandbox runs a trivial build/test job end-to-end |

## 11.2 Release R1 — CSE/IT MVP (Sprints 3–7)

| Sprint | Goals | Key deliverables |
| --- | --- | --- |
| Sprint 3 | Static analysis + test execution stage of CSE/IT evaluator | Automated lint/complexity + hidden-test-suite execution producing sub-scores |
| Sprint 4 | Security scan stage + AI/LLM Gateway v1 | SAST/dependency scan integrated; Gateway with prompt versioning live for one evaluator call |
| Sprint 5 | LLM-based architecture/code review stage; Scoring & Rubric Engine v1 | Full CSE/IT scorecard assembled from all sub-stages with evidence |
| Sprint 6 | Expert Review console v1 + calibration event logging | Experts can review/override a CSE/IT scorecard; overrides logged |
| Sprint 7 | Student portal polish (submission flow, results view), first 10–15 CSE/IT projects authored & expert-approved | R1 demo: full CSE/IT journey live end-to-end; sign-off with CSE/IT expert panel |

## 11.3 Release R2 — AI/ML & Data Science track (Sprints 8–10)

| Sprint | Goals | Key deliverables |
| --- | --- | --- |
| Sprint 8 | Notebook execution sandbox + held-out evaluation harness | Notebooks run headless; metrics computed against hidden test split |
| Sprint 9 | Data-leakage/methodology checks + robustness/bias checks | Automated flags for leakage & subgroup performance; LLM report review stage |
| Sprint 10 | AI/ML scorecard assembly, expert calibration for this track, first 8–10 projects authored & approved | R2 demo & sign-off with AI/ML expert panel |

## 11.4 Release R3 — Core Engineering tracks (Sprints 11–16)

| Sprint | Goals | Key deliverables |
| --- | --- | --- |
| Sprint 11 | Recruit/onboard ECE/EEE/Mechanical/Automobile expert panels; finalize core-eng rubric templates | Approved rubric templates per branch; artifact-format specs (CAD/schematic/report/video) |
| Sprint 12 | Artifact parsing adapters: CAD (STEP/DXF), schematic/netlist | Structural completeness checks for ECE/EEE/Mech/Auto submissions |
| Sprint 13 | Simulation-result validation stage (tolerance-band comparison) | Automated pass/fail on declared simulation outputs vs. rubric tolerances |
| Sprint 14 | Standards/checklist compliance engine + vision-model schematic/drawing review | Compliance sub-score; multimodal design-review notes |
| Sprint 15 | Design-report LLM review + mandatory human-review gating logic | Report sub-score; enforced expert sign-off before any core-eng “pass” |
| Sprint 16 | First 5–10 projects per core branch authored & expert-approved; end-to-end core-eng journey | R3 demo & sign-off with core-engineering expert panels |

## 11.5 Release R4 — Expert & Company ecosystem (Sprints 17–19)

| Sprint | Goals | Key deliverables |
| --- | --- | --- |
| Sprint 17 | Expert marketplace: application, credential verification, domain tagging, payouts integration | Self-serve expert onboarding; payment gateway wired for payouts |
| Sprint 18 | Calibration loop automation (weekly aggregation, AI-confidence scoring per project) | Dashboard showing per-project AI confidence & sampling-rate adjustment |
| Sprint 19 | Company Partner Portal: brief authoring, NDA workflow, talent search & filtering | Pilot company can publish a brief and view a ranked, scored candidate list |

## 11.6 Release R5 — Credentialing, analytics & scale hardening (Sprints 20–22)

| Sprint | Goals | Key deliverables |
| --- | --- | --- |
| Sprint 20 | Credential/portfolio public pages, verifiable-credential format | Shareable, verifiable per-project and cumulative readiness credentials |
| Sprint 21 | College/Placement Cell console + analytics warehouse & dashboards | Cohort dashboards; admin/company/college reporting live |
| Sprint 22 | Load/security hardening: penetration test on sandbox isolation, deadline-day load test, cost-governance dashboards | Go-live readiness sign-off with business owner |

## 11.7 Parallel workstream — content & expert governance

Running throughout all releases, not a separate phase: the Industry Content/Curriculum Lead and the relevant expert panel author and approve new projects/rubrics ahead of each release's engineering work, so no evaluator pipeline is ever built against an unapproved rubric.

# 12. Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Core-engineering submissions are hard to fully automate; AI evaluation may be shallow at launch | Low trust in ECE/EEE/Mech/Auto scores | Deliberately weight these tracks toward human experts (Section 5.5); mandatory sign-off gating; expand automation only as confidence data accumulates |
| Students share solutions across cohorts/years | Score inflation, credential loses meaning | Parameterized project variants, unique per-assignment tokens, plagiarism/similarity checks, project rotation |
| Expert supply doesn't scale with student volume | Review backlog, missed SLAs, disengagement | Tiered AI-confidence-based sampling so only the highest-value reviews need experts; gig-style pay-per-review to attract supply |
| LLM/AI evaluation cost scales faster than revenue | Margin pressure, especially on compute-heavy core-eng pipeline | AI/LLM Gateway cost tracking per assessment; tiered model use (cheaper models for first-pass checks, stronger models only where needed) |
| Sandboxed execution of untrusted student code is compromised | Security incident, platform trust damage | Network-isolated ephemeral sandboxes, resource limits, regular penetration testing (Sprint 22 and ongoing) |
| Companies want highly proprietary/custom rubrics the generic engine can't score well | Company churn, unmet expectations | Company Portal explicitly supports custom rubric authoring plus a mandatory human-review fallback for novel rubric types |
| Colleges resist a platform that bypasses/embarrasses existing academic assessment | Slow adoption at institutional level | Position as a placement-readiness and outcome-evidence tool for the college (Section 4.6), not a replacement for academic grading |

# 13. Success Metrics (KPIs)

## 13.1 Product/engagement KPIs

- Student activation rate (sign-up → first project submitted).

- Project completion rate within the 48-hour window, by branch.

- Average AI-confidence score per track (proxy for automation maturity).

- Expert review SLA adherence and reviewer utilization.

## 13.2 Quality/trust KPIs

- Expert override rate per project (should trend down as calibration improves, or flag a rubric problem if it doesn't).

- Dispute rate and dispute-resolution turnaround time.

- Plagiarism/integrity flag rate.

## 13.3 Business KPIs

- Number of active company partners and briefs published.

- Candidate-to-hire conversion rate sourced through the platform (where trackable).

- College partnerships and cohort enrollment volume.

- Cost per assessment (AI compute + expert payout) vs. revenue per student/company.

# 14. Glossary

| Term | Meaning |
| --- | --- |
| Rubric | Machine-readable set of weighted criteria used identically by the AI evaluator and the human expert to score a submission |
| Scorecard | The structured, evidence-backed output of an assessment: sub-scores, pass/fail, and supporting evidence |
| AI Confidence | A per-project score reflecting how reliable AI-only evaluation has proven to be, based on historical expert agreement |
| Evaluator | A domain-specific service (CSE/IT, AI/ML, Core-Engineering) that runs the checks defined in Section 5 |
| Calibration loop | The feedback process where expert overrides are used to tune evaluator behavior and rubric clarity over time |
| Sandbox | An isolated, ephemeral compute environment used to safely build/run/test untrusted student-submitted code |
| Credential | A verifiable, shareable record of a passed project or cumulative readiness score, intended for resumes/LinkedIn |